## Summary
Phase | Done | Open | Bugs | Total | % Complete
Phase 0: Foundation | 13 | 0 | 0 | 13 | 100%
Phase 1: Layout & Core Widgets | 10 | 0 | 0 | 10 | 100%
Phase 2: Touch Refinement | 17 | 7 | 2 | 26 | 65.38%
Phase 3: Visual Polish & UX | 30 | 6 | 2 | 38 | 78.95%
Phase 4: New Widgets | 0 | 55 | 0 | 55 | 0%
Phase 5: Hardware Control | 0 | 7 | 0 | 7 | 0%
Phase 6: Spotify Web API Integration | 0 | 8 | 0 | 8 | 0%
Phase 7: Licensing & Commercial Distribution (Paddle) | 0 | 32 | 0 | 32 | 0%
Phase 8: App Hardening & Reliability | 0 | 21 | 1 | 22 | 0%
TOTAL | 70 | 136 | 5 | 211 | 33.18%

## All Items
Phase | Section | Status | Item
Phase 0: Foundation |  | Done | Create Xcode project (macOS app, Swift, SwiftUI lifecycle with AppKit bridge)
Phase 0: Foundation |  | Done | Implement `LedgePanel` (NSPanel subclass with `.nonactivatingPanel`)
Phase 0: Foundation |  | Done | Detect the Xeneon Edge among connected screens (by resolution or name)
Phase 0: Foundation |  | Done | Display the panel fullscreen on the Xeneon Edge
Phase 0: Foundation |  | Done | Handle display connect/disconnect gracefully
Phase 0: Foundation |  | Done | Add settings window on the primary display (NavigationSplitView with sidebar)
Phase 0: Foundation |  | Done | Build basic Clock widget (validates the widget system)
Phase 0: Foundation |  | Done | Build touch test view
Phase 0: Foundation |  | Done | Implement TouchRemapper (CGEventTap) to fix macOS touchscreen coordinate mapping
Phase 0: Foundation |  | Done | Auto-detect touchscreen device via IOKit HID (HIDTouchDetector)
Phase 0: Foundation |  | Done | App Sandbox disabled (`ENABLE_APP_SANDBOX = NO`)
Phase 0: Foundation |  | Done | Accessibility permission request/polling flow with auto-retry
Phase 0: Foundation |  | Done | Display security: blank panel on sleep/lock/screensaver, restore on unlock/wake
Phase 1: Layout & Core Widgets |  | Done | Implement 20×6 grid layout engine (`GridRenderer`, `LayoutManager`, `LayoutModels`)
Phase 1: Layout & Core Widgets |  | Done | `WidgetRegistry` singleton with type registration and view factories
Phase 1: Layout & Core Widgets |  | Done | `WidgetContext` per-instance with size and config store
Phase 1: Layout & Core Widgets |  | Done | `WidgetConfigStore` for per-widget persistent configuration (JSON)
Phase 1: Layout & Core Widgets |  | Done | Widget placement from JSON layout files (`~/Library/Application Support/Ledge/`)
Phase 1: Layout & Core Widgets |  | Done | Layout editing: interactive grid editor in Settings with drag, resize, remove
Phase 1: Layout & Core Widgets |  | Done | Settings UI: widget picker (gallery with cards, categories, search), layout preview
Phase 1: Layout & Core Widgets |  | Done | Multiple saved layouts with create/switch/delete (LayoutManager)
Phase 1: Layout & Core Widgets |  | Done | Layout migration (auto-scales old 10×3 layouts to 20×6)
Phase 1: Layout & Core Widgets |  | Done | Theme system: 5 built-in themes (Dark, Light, Midnight, Ocean, Forest), auto mode
Phase 2: Touch Refinement | Current Approach: Direct NSEvent Delivery | Done | CGEventTap intercepts touchscreen events (identified by HID device ID)
Phase 2: Touch Refinement | Current Approach: Direct NSEvent Delivery | Done | Coordinate remapping from primary display CG space to Edge CG space
Phase 2: Touch Refinement | Current Approach: Direct NSEvent Delivery | Done | Suppress original events (return nil from callback)
Phase 2: Touch Refinement | Current Approach: Direct NSEvent Delivery | Done | Direct NSEvent delivery to LedgePanel (bypasses window server)
Phase 2: Touch Refinement | Current Approach: Direct NSEvent Delivery | Done | Asynchronous delivery via `DispatchQueue.main.async` (avoids run loop deadlock)
Phase 2: Touch Refinement | Current Approach: Direct NSEvent Delivery | Done | `NSApp.preventWindowOrdering()` before each delivery
Phase 2: Touch Refinement | Current Approach: Direct NSEvent Delivery | Done | mouseMoved suppression (touchscreen hover noise)
Phase 2: Touch Refinement | Current Approach: Direct NSEvent Delivery | Done | Diagnostic logging at `.notice` level with sequence IDs
Phase 2: Touch Refinement | Current Approach: Direct NSEvent Delivery | Done | Automatic permission polling + re-request on app activation
Phase 2: Touch Refinement | Touch Diagnostics & Testing Infrastructure | Done | TouchCoordinateMath
Phase 2: Touch Refinement | Touch Diagnostics & Testing Infrastructure | Done | TouchFlightRecorder
Phase 2: Touch Refinement | Touch Diagnostics & Testing Infrastructure | Done | TouchWatchdog
Phase 2: Touch Refinement | Touch Diagnostics & Testing Infrastructure | Done | Delivery confirmation
Phase 2: Touch Refinement | Touch Diagnostics & Testing Infrastructure | Done | Touch Diagnostics widget (`com.ledge.touch-diagnostics`)
Phase 2: Touch Refinement | Touch Diagnostics & Testing Infrastructure | Done | Panel alignment bug fix
Phase 2: Touch Refinement | Touch Diagnostics & Testing Infrastructure | Done | XCTest target
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Bug | Stability: Touch mapping occasionally drops or crashes
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Bug | Focus stealing (CRITICAL): Active application loses focus when touching the Edge. This is the #1 usability blocker. The `.nonactivatingPanel` + direct NSEvent delivery approach should prevent this, but something is still activating the app. Investigate: (a) `panel.makeKey()` in `mouseDown`
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Open | Mouse cursor guard: When the mouse (not touch) drifts onto the Edge display, it can interact with widgets. Options: (a) invisible barrier that warps cursor back, (b) ignore mouse-sourced events on the Edge, (c) leave it for Web widget convenience. Decision pending
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Open | Touch disable toggle: Settings UI toggle to completely disable the touch event tap. Placed alongside the existing Event Tap settings. Useful for: (a) preventing accidental touches, (b) using mouse-only mode on the Edge, (c) troubleshooting touch issues. When disabled, the CGEventTap is torn down entirely
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Open | Touch visual indicator: Visual feedback when the screen is touched
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Open | Long-running gestures: Volume/progress slider drags work but need more testing for reliability
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Open | Event tap recovery: If the CGEventTap is disabled by the system (timeout or user input), it re-enables
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Open | Multi-touch: Not available on macOS via USB touchscreen
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Open | Comprehensive testing: Systematic test plan needed
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Done | Separate Spaces per display: Resolved
Phase 3: Visual Polish & UX | Spotify Widget Polish | Done | Album art crossfade/fade-out-in on track change, synchronised with background colour transition
Phase 3: Visual Polish & UX | Spotify Widget Polish | Done | Centered playback controls with 44pt touch targets
Phase 3: Visual Polish & UX | Spotify Widget Polish | Done | Larger text fonts for touchscreen readability
Phase 3: Visual Polish & UX | Spotify Widget Polish | Done | Marquee text with overflow threshold fix (no scroll when text fits)
Phase 3: Visual Polish & UX | Spotify Widget Polish | Done | Left-to-right text reveal animation on track change
Phase 3: Visual Polish & UX | Visual Design | Done | Transparent widget backgrounds with blur
Phase 3: Visual Polish & UX | Visual Design | Done | Liquid Glass design language
Phase 3: Visual Polish & UX | Visual Design | Done | Background images
Phase 3: Visual Polish & UX | Visual Design | Done | Widget transitions
Phase 3: Visual Polish & UX | Visual Design | Done | Desktop wallpaper fallback
Phase 3: Visual Polish & UX | Fullscreen Display Management | Done | Native fullscreen via helper window
Phase 3: Visual Polish & UX | Fullscreen Display Management | Done | Independent Spaces support
Phase 3: Visual Polish & UX | Fullscreen Display Management | Done | Accessibility permission gate
Phase 3: Visual Polish & UX | Multiple Pages (Swipeable Layouts) | Done | Page indicator on the Edge (dot-style capsule, fades in on page switch, subtle at rest)
Phase 3: Visual Polish & UX | Multiple Pages (Swipeable Layouts) | Done | Swipe gesture to switch between saved layouts (dampened drag + threshold, wraps around)
Phase 3: Visual Polish & UX | Multiple Pages (Swipeable Layouts) | Done | `LayoutManager` page navigation: `nextPage()`, `previousPage()`, `switchToPage(_:)`, `activePageIndex`, `pageCount`
Phase 3: Visual Polish & UX | Multiple Pages (Swipeable Layouts) | Done | Optional auto-rotation on timer
Phase 3: Visual Polish & UX | Multiple Pages (Swipeable Layouts) | Done | Per-page background image support
Phase 3: Visual Polish & UX | Multiple Pages (Swipeable Layouts) | Done | Consolidated "Widgets & Layout" settings panel
Phase 3: Visual Polish & UX | Widget Gallery & Settings Improvements | Done | Visual card-based gallery with 2-column grid
Phase 3: Visual Polish & UX | Widget Gallery & Settings Improvements | Done | Category filtering (Media, Productivity, System, Smart Home, Info, Web)
Phase 3: Visual Polish & UX | Widget Gallery & Settings Improvements | Done | Search bar
Phase 3: Visual Polish & UX | Widget Gallery & Settings Improvements | Done | "Already added" badges
Phase 3: Visual Polish & UX | Widget Gallery & Settings Improvements | Done | Hover effects and category-coloured icons
Phase 3: Visual Polish & UX | Widget Gallery & Settings Improvements | Done | Widget preview thumbnails
Phase 3: Visual Polish & UX | Widget Gallery & Settings Improvements | Done | Widget position/size controls (DisclosureGroup, collapsed by default
Phase 3: Visual Polish & UX | Widget Gallery & Settings Improvements | Done | Widget-specific settings accessible from layout editor
Phase 3: Visual Polish & UX | Widget Gallery & Settings Improvements | Done | System Performance widget data persistence
Phase 3: Visual Polish & UX | Widget Gallery & Settings Improvements | Done | Grid editor drag/resize jitter fix
Phase 3: Visual Polish & UX | Widget Gallery & Settings Improvements | Done | Settings panel reliability
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | Widget configuration from the layout editor (tap a placed widget → settings popover on the Edge itself, not just Settings window)
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Bug | Panel position bug on display config change
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | Background mode override
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | Tighter widget grid gap
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | Weather widget
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Bug | Spotify marquee text bug
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | DateTime widget
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | System Performance
Phase 4: New Widgets | App Launcher (Stream Deck Style) | Open | Configurable button grid
Phase 4: New Widgets | App Launcher (Stream Deck Style) | Open | Per-button configuration: app to launch, system action, keyboard shortcut, URL, or script
Phase 4: New Widgets | App Launcher (Stream Deck Style) | Open | Button appearance: custom icon (SF Symbols or image), label, background colour
Phase 4: New Widgets | App Launcher (Stream Deck Style) | Open | Transparent glass-effect button background (consistent with Liquid Glass theme)
Phase 4: New Widgets | App Launcher (Stream Deck Style) | Open | Press animation (scale/highlight feedback for touch)
Phase 4: New Widgets | App Launcher (Stream Deck Style) | Open | App launching via `NSWorkspace.shared.open()` / `Process` for scripts
Phase 4: New Widgets | App Launcher (Stream Deck Style) | Open | Investigate Stream Deck SDK compatibility for shared configurations
Phase 4: New Widgets | App Launcher (Stream Deck Style) | Open | Folder/group support (tap to expand a group of related buttons)
Phase 4: New Widgets | MS Teams Integration | Open | Detect active Teams meeting in the PWA (AppleScript to browser)
Phase 4: New Widgets | MS Teams Integration | Open | Mic mute/unmute toggle
Phase 4: New Widgets | MS Teams Integration | Open | Camera on/off toggle
Phase 4: New Widgets | MS Teams Integration | Open | Visual indicator for screen sharing (bold flashing border around a widget)
Phase 4: New Widgets | MS Teams Integration | Open | Meeting status display (in meeting / not in meeting / presenting)
Phase 4: New Widgets | MS Teams Integration | Open | Also investigate the full MS Teams desktop client (different approach may be needed)
Phase 4: New Widgets | Calendar Improvements | Open | Respect visible calendars only
Phase 4: New Widgets | Calendar Improvements | Open | Meeting type detection
Phase 4: New Widgets | Calendar Improvements | Open | Meeting quick-join
Phase 4: New Widgets | Calendar Improvements | Open | Meeting controls integration
Phase 4: New Widgets | Calendar Improvements | Open | Screen sharing indicator
Phase 4: New Widgets | Calendar Improvements | Open | Google Calendar direct integration
Phase 4: New Widgets | Web Widget Improvements | Open | Touch scroll support
Phase 4: New Widgets | Web Widget Improvements | Open | Swipe navigation
Phase 4: New Widgets | Web Widget Improvements | Open | Scroll position persistence
Phase 4: New Widgets | Home Assistant Widget Improvements | Open | Faders/sliders for dimmable entities
Phase 4: New Widgets | Home Assistant Widget Improvements | Open | Custom display names
Phase 4: New Widgets | Home Assistant Widget Improvements | Open | Entity grouping
Phase 4: New Widgets | Home Assistant Widget Improvements | Open | RGB colour picker
Phase 4: New Widgets | Home Assistant Widget Improvements | Open | Cover controls
Phase 4: New Widgets | Home Assistant Widget Improvements | Open | Sensor display
Phase 4: New Widgets | System Audio Widget Improvements | Open | Layout redesign
Phase 4: New Widgets | System Audio Widget Improvements | Open | Larger button touch targets
Phase 4: New Widgets | System Audio Widget Improvements | Open | Visual feedback on tap
Phase 4: New Widgets | Game/App Companion Dashboards | Open | Framework for full-page app companions
Phase 4: New Widgets | Game/App Companion Dashboards | Open | Game data ingestion
Phase 4: New Widgets | Game/App Companion Dashboards | Open | Example: macOS-native game companion
Phase 4: New Widgets | Game/App Companion Dashboards | Open | Community/plugin angle
Phase 4: New Widgets | Game/App Companion Dashboards | Open | Non-gaming companions
Phase 4: New Widgets | Context-Aware / App-Aware Widgets | Open | Active-app detection
Phase 4: New Widgets | Context-Aware / App-Aware Widgets | Open | App-specific shortcut panels
Phase 4: New Widgets | Context-Aware / App-Aware Widgets | Open | Auto-switching pages
Phase 4: New Widgets | Context-Aware / App-Aware Widgets | Open | Keyboard shortcut execution
Phase 4: New Widgets | Context-Aware / App-Aware Widgets | Open | App-aware widget states
Phase 4: New Widgets | Other Widget Ideas | Open | OBS Studio widget (scene switching, stream status)
Phase 4: New Widgets | Other Widget Ideas | Open | Network monitor (bandwidth, latency, connected devices)
Phase 4: New Widgets | Other Widget Ideas | Open | Clipboard history
Phase 4: New Widgets | Other Widget Ideas | Open | Countdown timer / Pomodoro
Phase 4: New Widgets | Other Widget Ideas | Open | Notes / sticky notes
Phase 4: New Widgets | Other Widget Ideas | Open | System shortcuts (sleep, lock, screenshot, Do Not Disturb toggle)
Phase 4: New Widgets | Other Widget Ideas | Open | Photos slideshow widget
Phase 4: New Widgets | Other Widget Ideas | Open | Notifications widget / toast system
Phase 4: New Widgets | Other Widget Ideas | Open | Persistent bottom ticker strip
Phase 4: New Widgets | Other Widget Ideas | Open | News ticker widget
Phase 4: New Widgets | Other Widget Ideas | Open | Stock ticker / watchlist widget
Phase 4: New Widgets | Other Widget Ideas | Open | Flight Radar widget
Phase 4: New Widgets | Other Widget Ideas | Open | Carrot Weather widget
Phase 5: Hardware Control | Other Widget Ideas | Open | Test DDC/CI brightness control (DDC confirmed working via MonitorControl)
Phase 5: Hardware Control | Other Widget Ideas | Open | Implement brightness/contrast sliders
Phase 5: Hardware Control | Other Widget Ideas | Open | Investigate Corsair-specific USB HID protocol for colour profiles
Phase 5: Hardware Control | Other Widget Ideas | Open | Build a Display Controls widget
Phase 5: Hardware Control | Other Widget Ideas | Open | Set up Wireshark + USBPcap on Windows for protocol capture
Phase 5: Hardware Control | Other Widget Ideas | Open | Document HID reports in `docs/USB_PROTOCOL.md`
Phase 5: Hardware Control | Other Widget Ideas | Open | Investigate: does iCUE send pixel data via USB, or render on-monitor?
Phase 6: Spotify Web API Integration | Implementation | Open | Create `SpotifyAuthManager`
Phase 6: Spotify Web API Integration | Implementation | Open | Create `SpotifyAPIBridge`
Phase 6: Spotify Web API Integration | Implementation | Open | Device selector in Spotify widget
Phase 6: Spotify Web API Integration | Implementation | Open | "Playing on [device]" indicator when music is on another device
Phase 6: Spotify Web API Integration | Implementation | Open | Album art via URL (cleaner than extracting from local app)
Phase 6: Spotify Web API Integration | Implementation | Open | Keep AppleScript bridge as fallback for users without Spotify Premium or who prefer local-only
Phase 6: Spotify Web API Integration | Implementation | Open | Settings toggle: "Use Spotify Web API" vs "Use local Spotify app"
Phase 6: Spotify Web API Integration | Implementation | Open | Handle token expiry, network errors, and rate limiting gracefully
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle Account & Product Setup | Open | Create Paddle seller account
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle Account & Product Setup | Open | Create product in Paddle dashboard
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle Account & Product Setup | Open | Configure license key settings
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle Account & Product Setup | Open | Configure trial settings
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle Account & Product Setup | Open | Tax setup
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle Account & Product Setup | Open | Webhook endpoints (optional)
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle SDK Integration (In-App) | Open | Add Paddle macOS SDK
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle SDK Integration (In-App) | Open | License check at launch
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle SDK Integration (In-App) | Open | Trial implementation
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle SDK Integration (In-App) | Open | Activation flow
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle SDK Integration (In-App) | Open | Deactivation
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle SDK Integration (In-App) | Open | Offline grace period
Phase 7: Licensing & Commercial Distribution (Paddle) | Paddle SDK Integration (In-App) | Open | License status in Settings
Phase 7: Licensing & Commercial Distribution (Paddle) | Trial & Purchase UX | Open | First launch (no license)
Phase 7: Licensing & Commercial Distribution (Paddle) | Trial & Purchase UX | Open | During trial
Phase 7: Licensing & Commercial Distribution (Paddle) | Trial & Purchase UX | Open | Trial expired
Phase 7: Licensing & Commercial Distribution (Paddle) | Trial & Purchase UX | Open | Post-purchase
Phase 7: Licensing & Commercial Distribution (Paddle) | Trial & Purchase UX | Open | Pricing model decision
Phase 7: Licensing & Commercial Distribution (Paddle) | Website & Landing Page | Open | Domain
Phase 7: Licensing & Commercial Distribution (Paddle) | Website & Landing Page | Open | Landing page
Phase 7: Licensing & Commercial Distribution (Paddle) | Website & Landing Page | Open | Download page
Phase 7: Licensing & Commercial Distribution (Paddle) | Website & Landing Page | Open | Support page
Phase 7: Licensing & Commercial Distribution (Paddle) | Website & Landing Page | Open | Privacy Policy
Phase 7: Licensing & Commercial Distribution (Paddle) | Website & Landing Page | Open | Terms of Service / EULA
Phase 7: Licensing & Commercial Distribution (Paddle) | Website & Landing Page | Open | Static site generator
Phase 7: Licensing & Commercial Distribution (Paddle) | Code Signing, Notarisation & Packaging | Open | Apple Developer Program
Phase 7: Licensing & Commercial Distribution (Paddle) | Code Signing, Notarisation & Packaging | Open | Code signing
Phase 7: Licensing & Commercial Distribution (Paddle) | Code Signing, Notarisation & Packaging | Open | Hardened Runtime
Phase 7: Licensing & Commercial Distribution (Paddle) | Code Signing, Notarisation & Packaging | Open | Notarisation
Phase 7: Licensing & Commercial Distribution (Paddle) | Code Signing, Notarisation & Packaging | Open | DMG packaging
Phase 7: Licensing & Commercial Distribution (Paddle) | Code Signing, Notarisation & Packaging | Open | Automated build pipeline
Phase 7: Licensing & Commercial Distribution (Paddle) | Code Signing, Notarisation & Packaging | Open | Sparkle auto-update
Phase 8: App Hardening & Reliability | First-Run Experience | Open | Onboarding flow
Phase 8: App Hardening & Reliability | First-Run Experience | Open | Graceful degradation
Phase 8: App Hardening & Reliability | First-Run Experience | Open | Permission health check
Phase 8: App Hardening & Reliability | Error Recovery & Crash Resilience | Open | CGEventTap recovery
Phase 8: App Hardening & Reliability | Error Recovery & Crash Resilience | Open | Corrupt data recovery
Phase 8: App Hardening & Reliability | Error Recovery & Crash Resilience | Bug | Crash reporting
Phase 8: App Hardening & Reliability | Error Recovery & Crash Resilience | Open | Watchdog for widget hangs
Phase 8: App Hardening & Reliability | Security & Data | Open | Keychain storage
Phase 8: App Hardening & Reliability | Security & Data | Open | Input validation
Phase 8: App Hardening & Reliability | Security & Data | Open | Memory & CPU budgets
Phase 8: App Hardening & Reliability | Performance | Open | Profiling
Phase 8: App Hardening & Reliability | Performance | Open | Instruments profiling for memory leaks, especially in long-running widget timers and album art caching
Phase 8: App Hardening & Reliability | Performance | Open | Stress testing
Phase 8: App Hardening & Reliability | Performance | Open | Launch time
Phase 8: App Hardening & Reliability | Accessibility & Polish | Open | VoiceOver labels for Settings UI, keyboard navigation in Settings
Phase 8: App Hardening & Reliability | Accessibility & Polish | Open | Layout sharing
Phase 8: App Hardening & Reliability | Accessibility & Polish | Open | Versioning
Phase 8: App Hardening & Reliability | Legal & Compliance | Open | Privacy Policy (required for notarisation, Paddle, and API integrations)
Phase 8: App Hardening & Reliability | Legal & Compliance | Open | Spotify branding compliance
Phase 8: App Hardening & Reliability | Legal & Compliance | Open | Home Assistant attribution if applicable
Phase 8: App Hardening & Reliability | Legal & Compliance | Open | WeatherKit attribution requirements
Phase 8: App Hardening & Reliability | Legal & Compliance | Open | EULA / Terms of Service

## Bugs & Polish
Phase | Section | Status | Item
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Bug | Stability: Touch mapping occasionally drops or crashes
Phase 2: Touch Refinement | Touch Known Issues & Open Work | Bug | Focus stealing (CRITICAL): Active application loses focus when touching the Edge. This is the #1 usability blocker. The `.nonactivatingPanel` + direct NSEvent delivery approach should prevent this, but something is still activating the app. Investigate: (a) `panel.makeKey()` in `mouseDown`
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Bug | Panel position bug on display config change
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Bug | Spotify marquee text bug
Phase 8: App Hardening & Reliability | Error Recovery & Crash Resilience | Bug | Crash reporting
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | Widget configuration from the layout editor (tap a placed widget → settings popover on the Edge itself, not just Settings window)
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | Background mode override
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | Tighter widget grid gap
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | Weather widget
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | DateTime widget
Phase 3: Visual Polish & UX | Remaining Polish (Future) | Open | System Performance